Ribble Valley Borough Council                                                                  

DELEGATED ITEM FILE REPORT - APPROVAL

	Ref: CS/EL

	Application No: 
	3/2007/0147/P

	Development Proposed:
	Variation of condition 2 of permission 3/91/726 to allow the period authorised for land filling operations to be extended until August 2007 and to allow the period authorised for final restoration of the site to be extended until August 2008 at Coplow Quarry, Clitheroe 

	CONSULTATIONS: Parish/Town Council

	Town Council - No objections to this proposal. 



	CONSULTATIONS: Highway/Water Authority/Other Bodies

	N/A



	CONSULTATIONS: Additional Representations.

	None received.



	RELEVANT POLICIES:

	Policy G1 - Development Control.

Policy ENV3 - Development in Open Countryside.

Policy ENV8 - Sites of Special Scientific Interest.

Policy ENV9 - Important Wildlife Site



	COMMENTS/ENVIRONMENTAL/AONB/HUMAN RIGHTS ISSUES/RECOMMENDATION:

	This is an application to be determined by Lancashire County Council upon which this Council has been consulted.  

Coplow Quarry is used for the depositing of waste material arising out of the cement making process, planning permission for which was granted under reference 3/91/726 on 19 February 1992.  Condition No 2 of that permission required the land filling operations to be discontinued after a period of 15 years (ie by 19 February 2007) and the approved restoration works to be completed within 16 years (ie by 19 February 2008).  This application seeks to extend each of those deadlines by six months to August 2007 and August 2008 respectively.  

I am not aware that the operations at this quarry have caused any serious problems to nearby residents over the last 15 years and can therefore see no objections to the relatively short extension of the two time periods.  



	RECOMMENDATION: That Lancashire County Council be informed that this Council has no objections to this application 


DATE INSPECTED: 














